## Multi-Campaign Tracker
Campaign | Task | Channel | Owner | Due Date | Priority | Status
Trailhead Launch | Approve final ad creative | Paid | Tariq Aziz | 2026-08-28 | High | In Progress
Trailhead Launch | Landing page copy review | Web | Meg Liu | 2026-09-01 | High | In Progress
Trailhead Launch | Press pitches out | PR | April Chen | 2026-08-29 | High | In Progress
Trailhead Launch | Launch email scheduled | Email | Meg Liu | 2026-09-09 | High | Not Started
Trailhead Launch | Partner reels confirmed | Social | Jess Moran | 2026-09-03 | Medium | In Progress
Trailhead Launch | Pop-up staffing locked | Event | Jess Moran | 2026-09-06 | Medium | Not Started
Harvest Sale | Offer and window signed off | Content | Noa Berg | 2026-08-24 | High | Done
Harvest Sale | Sale landing page build | Web | Riley Park | 2026-09-08 | Medium | In Progress
Harvest Sale | Announcement email draft | Email | Noa Berg | 2026-09-10 | Medium | Not Started
Harvest Sale | Promo codes tested | Web | Riley Park | 2026-09-16 | High | Not Started
Harvest Sale | Local press pitch | PR | Noa Berg | 2026-09-05 | Low | In Progress
Newsletter Revamp | New template design | Email | Cole Bennett | 2026-08-26 | Medium | Blocked
Newsletter Revamp | Migrate the welcome series | Email | Meg Liu | 2026-09-12 | Medium | Not Started
Newsletter Revamp | Archive page refresh | Web | Drew Santos | 2026-09-19 | Low | Not Started
Newsletter Revamp | Re-permission the lapsed segment | Email | Meg Liu | 2026-09-26 | Medium | Not Started
Trailhead Launch | Day-one metrics recap | Content | Jess Moran | 2026-09-11 | Medium | Not Started
Harvest Sale | Sale wrap-up report | Content | Noa Berg | 2026-09-24 | Low | Not Started
Newsletter Revamp | First send on the new template | Email | Meg Liu | 2026-10-01 | High | Not Started