## Simple Campaign Tracker
Task | Channel | Owner | Due Date | Status | Notes
Pick the sale window and offer | Content | Noa Berg | 2026-08-24 | Done | 20 percent off fall roasts, Sept 18 to 22
Write the sale landing page | Web | Riley Park | 2026-09-08 | In Progress | Reuses last season's layout
Shoot the seasonal product photos | Content | Sam Otieno | 2026-09-04 | In Progress | Morning light, in the roastery
Draft the announcement email | Email | Noa Berg | 2026-09-10 | Not Started | Subject line A/B: two options
Build the reminder email | Email | Noa Berg | 2026-09-15 | Not Started | Sends day 3 of the sale
Schedule social teasers | Social | Riley Park | 2026-09-12 | Not Started | 3 posts, staggered over launch week
Brief the wholesale accounts | Email | Sam Otieno | 2026-09-09 | Not Started | Wholesale gets 48-hour early access
Update the cafe chalkboards | Event | Sam Otieno | 2026-09-17 | Not Started | Both locations
Set the promo codes live | Web | Riley Park | 2026-09-17 | Not Started | HARVEST20, single use per customer
Boost the announcement post | Paid | Noa Berg | 2026-09-18 | Not Started | Small spend, local radius only
Pitch the local food weekly | PR | Noa Berg | 2026-09-05 | In Progress | They covered the spring release
Sale-day social posts | Social | Riley Park | 2026-09-18 | Not Started | Feed post plus stories through the day
Mid-sale performance check | Content | Noa Berg | 2026-09-20 | Not Started | Code redemptions vs last season
Wrap-up recap and thank-you email | Email | Noa Berg | 2026-09-24 | Not Started | Include the next roast preview