## Change Order Form
Section | Detail | Cost Impact | Schedule Impact (Days)
Change Order No. | CO-014
Project | Maple Street Clinic Renovation
Owner | Maple Street Clinic (Karen Boyle, owner rep)
Contractor | Harding Construction
Date Issued | July 8, 2026
Description of Change | Owner-requested upgrade of lobby and corridor flooring from VCT to porcelain tile, per revised finish schedule A-601 R2
Add: Porcelain tile, material | 1,850 sq ft at $6.40 installed grade | 11840
Add: Tile labor and setting materials | Thinset, leveling, movement joints | 9250 | 4
Add: Floor prep | Grind and self-level existing slab | 3400 | 2
Deduct: VCT material and labor | Original spec flooring, credited | -6180
Add: Schedule impact, general conditions | Supervision and temporary protection, 6 added days | 2100
Total This Change Order | Contract sum and contract time adjusted as shown | 20410 | 6
Revised Contract Sum | Original $1,284,500 plus all approved change orders to date
Approval | Not valid until signed by Owner, Architect, and Contractor