## Change Order Log
CO # | Description | Requested By | Date Submitted | Cost Impact | Schedule Impact (Days) | Status
CO-001 | Unforeseen: abandoned fuel line under slab | Field / contractor | 2026-03-06 | 8400 | 5 | Approved
CO-002 | Owner: add second break room sink | Owner | 2026-03-18 | 2150 | 0 | Approved
CO-003 | Design: revised structural detail at canopy | Architect | 2026-03-27 | 5900 | 3 | Approved
CO-004 | Owner: upgrade lobby lighting package | Owner | 2026-04-08 | 12600 | 0 | Rejected
CO-005 | Code: fire-rated glazing at corridor 2 | AHJ plan review | 2026-04-15 | 7300 | 4 | Approved
CO-006 | Unforeseen: rock excavation at grease trap | Field / contractor | 2026-04-29 | 4150 | 2 | Approved
CO-007 | Owner: relocate reception millwork | Owner | 2026-05-11 | 3800 | 1 | Pending
CO-008 | Design: RFI 44, beam clash at mech shaft | Architect | 2026-05-20 | 6650 | 3 | Approved
CO-009 | Owner: add exterior signage circuits | Owner | 2026-06-01 | 1950 | 0 | Approved
CO-010 | Duplicate of CO-008, issued in error | Architect | 2026-06-03 | 0 | 0 | Void
CO-011 | Unforeseen: damaged sewer lateral | Field / contractor | 2026-06-16 | 9800 | 4 | Pending
CO-012 | Owner: security camera rough-in, 8 locations | Owner | 2026-06-25 | 5400 | 1 | Pending
CO-013 | Design: revised ADA ramp slope at entry | Architect | 2026-07-02 | 4700 | 3 | Pending
Approved to date | 7 of 13 change orders approved |  |  | 36500 | 17