## Change Order with Owner Approva
CO # | Description | Cost Impact | Schedule Impact (Days) | Approver | Decision | Decision Date
CO-101 | Add covered walkway at north entry | 21400 | 6 | Karen Boyle | Approved | 2026-05-08
CO-102 | Upgrade HVAC controls to DDC | 34800 | 0 | Karen Boyle | Approved | 2026-05-15
CO-103 | Substitute quartz counters for laminate | 6900 | 0 | Priya Anand | Approved | 2026-05-22
CO-104 | Add 4 EV-ready parking stalls | 18200 | 3 | Karen Boyle | Rejected | 2026-06-01
CO-105 | Revised landscape plan, drought package | 9400 | 0 | Priya Anand | Approved | 2026-06-05
CO-106 | Acoustic ceiling upgrade, open office | 12750 | 2 | Priya Anand | Pending
CO-107 | Generator pad and transfer switch rough-in | 15900 | 4 | Karen Boyle | Pending
CO-108 | Interior glazing at conference rooms | 22100 | 5 | Karen Boyle | Approved | 2026-06-19
CO-109 | Roof walkway pavers for maintenance access | 5300 | 1 | June Park | Approved | 2026-06-26
CO-110 | Additional data drops, 24 locations | 7850 | 2 | Ray Delgado | Pending
CO-111 | Monument sign foundation and power | 11600 | 3 | Karen Boyle | Pending
Summary | 6 approved, 4 awaiting owner decision | 99900