## Agency Client Onboarding Checkl
Task | Phase | Owner | Due | Done | Notes
Countersign agreement and file SOW | Kickoff | Maya Chen | 2026-07-13 | TRUE | Signed July 10
Send welcome pack and intro email | Kickoff | Maya Chen | 2026-07-13 | TRUE
Book kickoff call with stakeholders | Kickoff | Rosa Vega | 2026-07-15 | TRUE | July 16, 10am
Collect brand guidelines and assets | Access & Assets | Rosa Vega | 2026-07-17 | TRUE | Drive folder shared
Request ad account access | Access & Assets | Liam Doyle | 2026-07-17 | FALSE | Waiting on client admin
Request analytics and tag manager access | Access & Assets | Liam Doyle | 2026-07-17 | TRUE
Set up shared Slack channel | Kickoff | Maya Chen | 2026-07-15 | TRUE
Add client to billing system | Kickoff | Maya Chen | 2026-07-15 | TRUE | Net 30
Run kickoff call and capture goals | Kickoff | Maya Chen | 2026-07-16 | TRUE | Recording linked in notes
Audit current site and campaigns | Strategy | Liam Doyle | 2026-07-22 | FALSE
Draft 90-day strategy deck | Strategy | Maya Chen | 2026-07-27 | FALSE
Define KPIs and reporting cadence | Strategy | Rosa Vega | 2026-07-24 | FALSE | Monthly report, weekly pulse
Client review of strategy deck | Strategy | Maya Chen | 2026-07-29 | FALSE
Set up monthly reporting dashboard | Launch | Rosa Vega | 2026-07-31 | FALSE
Build campaign shells and naming | Launch | Liam Doyle | 2026-07-31 | FALSE
QA tracking end to end | Launch | Liam Doyle | 2026-08-04 | FALSE
Launch first campaign | Launch | Liam Doyle | 2026-08-05 | FALSE
Schedule week-2 check-in | Launch | Maya Chen | 2026-08-07 | FALSE
Send first performance snapshot | Launch | Rosa Vega | 2026-08-12 | FALSE
Internal retro on onboarding | Launch | Maya Chen | 2026-08-14 | FALSE