## Freelancer Client Onboarding Ch
Task | Done | Due | Waiting on Client | Notes
Send proposal and get signature | TRUE | 2026-07-08 | FALSE | Signed same day
Invoice 50 percent deposit | TRUE | 2026-07-09 | FALSE | Paid July 9
Send onboarding questionnaire | TRUE | 2026-07-09 | TRUE | Reminder sent July 11
Schedule kickoff call | TRUE | 2026-07-10 | FALSE | July 14, 2pm
Collect logins and access | FALSE | 2026-07-14 | TRUE | Still need hosting login
Collect brand assets and copy | FALSE | 2026-07-15 | TRUE
Set up project folder and doc | TRUE | 2026-07-10 | FALSE
Agree communication channel and cadence | FALSE | 2026-07-14 | FALSE | Proposing email + Friday update
Confirm scope and first milestone | FALSE | 2026-07-14 | FALSE
Add project dates to calendar | FALSE | 2026-07-15 | FALSE
Share timeline with client | FALSE | 2026-07-16 | FALSE
Start milestone 1 | FALSE | 2026-07-17 | FALSE
Book mid-project review | FALSE | 2026-07-28 | FALSE
Set reminder for final invoice | FALSE | 2026-08-15 | FALSE