## Phased Onboarding Plan with % C
Task | Owner | Start | Due | % Complete | Status
Phase 1: Kickoff and Planning | Clara Boone | 2026-07-06 | 2026-07-17 | 85 | In Progress
Contract executed and filed | Clara Boone | 2026-07-06 | 2026-07-07 | 100 | Complete
Stakeholder map and RACI | Nia Campbell | 2026-07-08 | 2026-07-10 | 100 | Complete
Kickoff workshop | Clara Boone | 2026-07-13 | 2026-07-13 | 100 | Complete
Success plan drafted and shared | Nia Campbell | 2026-07-14 | 2026-07-17 | 40 | In Progress
Phase 2: Environment Setup | Felix Ward | 2026-07-13 | 2026-07-31 | 45 | In Progress
Production workspace provisioned | Felix Ward | 2026-07-13 | 2026-07-15 | 100 | Complete
User roles and permissions configured | Felix Ward | 2026-07-16 | 2026-07-21 | 60 | In Progress
SSO and security review | Nia Campbell | 2026-07-20 | 2026-07-24 | 20 | In Progress
Data migration dry run | Felix Ward | 2026-07-27 | 2026-07-31 | 0 | Not Started
Phase 3: Training and Validation | Nia Campbell | 2026-08-03 | 2026-08-14 | 0 | Not Started
Admin training delivered | Nia Campbell | 2026-08-03 | 2026-08-05 | 0 | Not Started
End-user training sessions | Nia Campbell | 2026-08-06 | 2026-08-11 | 0 | Not Started
UAT scenarios executed | Felix Ward | 2026-08-10 | 2026-08-13 | 0 | Not Started
Go-live readiness review | Clara Boone | 2026-08-14 | 2026-08-14 | 0 | Not Started
Phase 4: Go-Live and Handoff | Clara Boone | 2026-08-17 | 2026-08-28 | 0 | Not Started
Production go-live | Felix Ward | 2026-08-17 | 2026-08-18 | 0 | Not Started
Hypercare window (5 days) | Nia Campbell | 2026-08-19 | 2026-08-25 | 0 | Not Started
30-day success review booked | Clara Boone | 2026-08-26 | 2026-08-27 | 0 | Not Started
Handoff to customer success | Clara Boone | 2026-08-28 | 2026-08-28 | 0 | Not Started