## SaaS Customer Onboarding Checkl
Step | Stage | Owner Team | Customer Action | Status | Target Date
Sales-to-onboarding handoff call | Welcome | Sales | FALSE | Complete | 2026-07-08
Send welcome email with plan summary | Welcome | Onboarding | FALSE | Complete | 2026-07-08
Assign onboarding manager | Welcome | Onboarding | FALSE | Complete | 2026-07-08
Confirm success criteria with champion | Welcome | Onboarding | TRUE | Complete | 2026-07-10
Provision workspace and seats | Setup | Onboarding | FALSE | Complete | 2026-07-10
Invite admin users | Setup | Onboarding | TRUE | In Progress | 2026-07-14
Configure SSO | Setup | Support | TRUE | In Progress | 2026-07-16
Import historical data | Setup | Onboarding | TRUE | Not Started | 2026-07-17
Connect first integration | Setup | Product | TRUE | Not Started | 2026-07-17
Admin training session | Activation | Onboarding | TRUE | Not Started | 2026-07-21
End-user training session | Activation | Onboarding | TRUE | Not Started | 2026-07-23
First live workflow running | Activation | Onboarding | TRUE | Not Started | 2026-07-24
Champion sends internal announcement | Activation | Sales | TRUE | Not Started | 2026-07-24
Week-2 usage review | Adoption | Onboarding | FALSE | Not Started | 2026-07-28
Resolve open setup tickets | Adoption | Support | FALSE | Not Started | 2026-07-30
30-day business review booked | Adoption | Sales | TRUE | Not Started | 2026-08-06
Success plan signed off | Adoption | Onboarding | TRUE | Not Started | 2026-08-08
Handoff to account management | Adoption | Sales | FALSE | Not Started | 2026-08-11