## Construction Budget
Cost Code | Category | Description | Budgeted | Actual to Date | Variance | % Spent
01-000 | General Conditions | Supervision, temp facilities, fencing | 148000 | 96400 | 51600 | 65
02-200 | Subcontract | Earthwork and grading | 212000 | 214800 | -2800 | 101
02-500 | Subcontract | Site utilities | 164000 | 158200 | 5800 | 96
03-300 | Subcontract | Concrete foundations and slabs | 486000 | 452100 | 33900 | 93
05-100 | Material | Structural steel package | 138000 | 141600 | -3600 | 103
06-100 | Labor | Rough carpentry and framing labor | 294000 | 121500 | 172500 | 41
06-110 | Material | Framing lumber and hardware | 232000 | 148900 | 83100 | 64
07-500 | Subcontract | Roofing and waterproofing | 176000 | 0 | 176000 | 0
08-400 | Material | Windows and storefront | 121000 | 36300 | 84700 | 30
09-250 | Subcontract | Drywall, taping, paint | 268000 | 0 | 268000 | 0
15-300 | Subcontract | Fire protection | 94000 | 8200 | 85800 | 9
15-400 | Subcontract | Plumbing | 187000 | 42800 | 144200 | 23
15-500 | Subcontract | HVAC | 246000 | 61500 | 184500 | 25
16-100 | Subcontract | Electrical | 259000 | 74200 | 184800 | 29
01-800 | Equipment | Crane and hoisting | 68000 | 51000 | 17000 | 75
Total |  | All cost codes | 3093000 | 1607500 | 1485500 | 52