## Construction Project Dashboard
Milestone / Work Item | Trade | Status | Start | Finish | % Complete
Mobilization and site fencing | Sitework | Green | 2026-03-02 | 2026-03-13 | 100
Mass grading and utilities | Sitework | Green | 2026-03-16 | 2026-04-24 | 100
Foundations, Building B | Concrete | Green | 2026-04-27 | 2026-06-05 | 100
Slab on grade, pours 1-3 | Concrete | Green | 2026-06-01 | 2026-06-26 | 100
Structural framing, floors 1-2 | Framing | Green | 2026-06-22 | 2026-07-31 | 55
Structural framing, floor 3 | Framing | Amber | 2026-07-27 | 2026-08-21 | 0
Roof dry-in | Roofing | Amber | 2026-08-24 | 2026-09-18 | 0
MEP rough-in, floors 1-2 | MEP | Green | 2026-07-20 | 2026-09-04 | 10
Fire sprinkler rough-in | MEP | Red | 2026-08-03 | 2026-09-11 | 0
Window and storefront install | Finishes | Green | 2026-09-14 | 2026-10-09 | 0
Drywall and paint, floors 1-2 | Finishes | Green | 2026-09-21 | 2026-11-06 | 0
Elevator installation | General | Amber | 2026-09-07 | 2026-10-30 | 0
Site paving and striping | Sitework | Green | 2026-10-12 | 2026-10-30 | 0
Final inspections and punch list | General | Green | 2026-11-09 | 2026-12-04 | 0
Certificate of occupancy | General | Green | 2026-12-07 | 2026-12-11 | 0
Owner turnover and closeout | General | Green | 2026-12-14 | 2026-12-18 | 0