## Excel Gantt Chart
Task | Owner | Phase | Start | Finish | Duration (Days) | Days From Kickoff | Status
Project kickoff and goals | Nadia Osei | Planning | 2026-08-03 | 2026-08-04 | 2 | 0 | Complete
Stakeholder interviews | Nadia Osei | Planning | 2026-08-05 | 2026-08-11 | 7 | 2 | Complete
Content audit | Owen Clarke | Planning | 2026-08-05 | 2026-08-14 | 10 | 2 | Complete
Sitemap and page inventory | Owen Clarke | Planning | 2026-08-12 | 2026-08-14 | 3 | 9 | Complete
Wireframes | Leo Marchetti | Design | 2026-08-17 | 2026-08-25 | 9 | 14 | Complete
Visual design system | Leo Marchetti | Design | 2026-08-19 | 2026-09-01 | 14 | 16 | Complete
Page template designs | Leo Marchetti | Design | 2026-08-26 | 2026-09-08 | 14 | 23 | Complete
Design review and sign-off | Nadia Osei | Design | 2026-09-09 | 2026-09-10 | 2 | 37 | In Progress
CMS setup and configuration | Priya Raman | Build | 2026-08-26 | 2026-09-04 | 10 | 23 | Complete
Front-end build, page templates | Priya Raman | Build | 2026-09-09 | 2026-09-22 | 14 | 37 | In Progress
Content migration, 60 pages | Owen Clarke | Build | 2026-09-11 | 2026-09-23 | 13 | 39 | Not Started
Integrations and forms | Priya Raman | Build | 2026-09-15 | 2026-09-22 | 8 | 43 | Not Started
QA and cross-browser pass | Tessa Boyd | Launch | 2026-09-23 | 2026-09-29 | 7 | 51 | Not Started
Accessibility and performance fixes | Tessa Boyd | Launch | 2026-09-28 | 2026-10-01 | 4 | 56 | Not Started
Stakeholder UAT | Nadia Osei | Launch | 2026-09-29 | 2026-10-02 | 4 | 57 | Not Started
Launch and DNS cutover | Priya Raman | Launch | 2026-10-05 | 2026-10-05 | 1 | 63 | Not Started
Post-launch monitoring | Tessa Boyd | Launch | 2026-10-06 | 2026-10-09 | 4 | 64 | Not Started