## Two Week Sprint Gantt
Task | Assignee | Start | Finish | Working Days | Starts On Day | Status
Sprint planning and task breakdown | Nadia Osei | 2026-09-07 | 2026-09-07 | 1 | 1 | Done
Build header and navigation template | Priya Raman | 2026-09-08 | 2026-09-10 | 3 | 2 | In Progress
Analytics and tag setup | Marco Diaz | 2026-09-08 | 2026-09-09 | 2 | 2 | Done
Build home page template | Priya Raman | 2026-09-11 | 2026-09-15 | 3 | 5 | To Do
Migrate first 20 pages of content | Owen Clarke | 2026-09-11 | 2026-09-16 | 4 | 5 | To Do
Mid-sprint review | Nadia Osei | 2026-09-11 | 2026-09-11 | 1 | 5 | To Do
Contact and demo request forms | Marco Diaz | 2026-09-15 | 2026-09-17 | 3 | 7 | To Do
Build article and landing templates | Priya Raman | 2026-09-16 | 2026-09-18 | 3 | 8 | To Do
QA smoke pass on built templates | Tessa Boyd | 2026-09-17 | 2026-09-18 | 2 | 9 | To Do
Sprint review and demo | Nadia Osei | 2026-09-18 | 2026-09-18 | 1 | 10 | To Do