## Executive Status One-Pager
Area | Status | Summary | Owner | Updated
Overall | Amber | On scope and budget; schedule pressure from vendor API slip | Paula Brandt | 2026-07-09
Schedule | Amber | Integration testing starts 8 days late; recovery plan in place | Dev Sharma | 2026-07-09
Budget | Green | $412K of $520K committed; contingency untouched | Grace Lin | 2026-07-08
Scope | Green | No open change requests this period | Paula Brandt | 2026-07-09
Risks | Amber | Top risk: cutover freeze overlaps peak season (score 12) | Dev Sharma | 2026-07-09
Quality | Green | UAT defect burn-down ahead of plan; zero sev-1 open | Lena Voss | 2026-07-08
Resourcing | Red | Data lead departs July 31; backfill not yet signed | Kate Muir | 2026-07-09
Milestone: UAT complete | Green | Done July 2, four days early | Lena Voss | 2026-07-02
Milestone: Integration test start | Amber | Now July 20 (was July 10), vendor API dependency | Dev Sharma | 2026-07-09
Milestone: Training complete | Green | On track for August 21 | Kate Muir | 2026-07-09
Milestone: Go-live | Amber | September 9 holds only if integration recovery lands | Paula Brandt | 2026-07-09
Decision needed | Red | Approve backfill offer for data lead by July 15 | Kate Muir | 2026-07-09
Decision needed | Amber | Accept 8-day test compression or move go-live to September 23 | Paula Brandt | 2026-07-09
Next period focus | Green | Close integration recovery plan; sign backfill; start training wave 1 | Paula Brandt | 2026-07-09