## Portfolio Status Report
Project | Sponsor | Phase | Health | Budget | % Complete | Next Milestone
ERP Phase 2 | Dana Whitfield | Execute | Amber | Green | 68 | Integration test start, Jul 20
Warehouse Automation Pilot | Elena Ruiz | Execute | Green | Green | 45 | Robot commissioning, Aug 3
Customer Portal Rebuild | Diane Foster | Execute | Green | Amber | 72 | Beta to 50 customers, Jul 24
Fleet Telematics Rollout | Jack Morrow | Plan | Green | Green | 15 | Vendor contract signature, Jul 17
Finance Close Automation | Grace Lin | Execute | Red | Amber | 55 | Reconciliation module UAT, Jul 31
Data Warehouse Migration | Bruno Keller | Execute | Amber | Green | 60 | Historical load complete, Aug 14
Retail POS Refresh | Lotte Brandt | Plan | Green | Green | 20 | Pilot store selection, Jul 22
Security Zero-Trust Program | Raj Patel | Execute | Green | Green | 38 | MFA wave 2 complete, Aug 7
HR Onboarding Redesign | Kate Muir | Close | Green | Green | 95 | Post-launch review, Jul 18
Supplier EDI Expansion | Marcus Lee | Initiate | Green | Green | 5 | Charter approval, Jul 25