## Weekly Status Report
Category | Item | Owner | Date
Accomplished | UAT cycle 2 closed: 41 of 44 scripts passed | Lena Voss | 2026-07-08
Accomplished | Vendor SOW amendment signed | Paula Brandt | 2026-07-07
Accomplished | Warehouse pick-path config validated at Reno | Omar Reyes | 2026-07-09
Accomplished | Training environment refreshed with July data | Dev Sharma | 2026-07-06
In Progress | Integration recovery plan with vendor API team | Dev Sharma | 2026-07-10
In Progress | Cutover runbook, draft 2 of 3 | Omar Reyes | 2026-07-10
In Progress | Training curriculum review with site leads | Kate Muir | 2026-07-10
Planned | Integration test kickoff | Dev Sharma | 2026-07-20
Planned | Steering committee, July session | Paula Brandt | 2026-07-28
Planned | Data reconciliation dry run | Lena Voss | 2026-07-23
Planned | Site readiness walkthrough, Boise | Omar Reyes | 2026-07-27
Blocker | Vendor sandbox still missing July patch; blocks 6 test scripts | Dev Sharma | 2026-07-09
Blocker | Two trainers unconfirmed for wave 1 | Kate Muir | 2026-07-09
Decision Needed | Backfill offer for departing data lead | Kate Muir | 2026-07-15
Decision Needed | Test compression vs go-live slip to September 23 | Paula Brandt | 2026-07-28
Accomplished | Executive one-pager adopted as the standing report format | Paula Brandt | 2026-07-06