## IT Incident Report
Incident ID | Date | System | Severity | User Impact | Root Cause | Resolution | Owner | Status
INC-1041 | 2026-07-03 | Checkout API | Sev 1 | Payments failing for 22 minutes | Expired TLS certificate on the payment gateway proxy | Certificate rotated; expiry monitoring alert added at 30 days | Priya Nair | Closed
INC-1042 | 2026-07-08 | Email service | Sev 3 | Outbound receipts delayed up to 2 hours | Queue worker OOM after a large campaign | Worker memory doubled; campaign batching capped | Sam Whitlock | Closed
INC-1043 | 2026-07-12 | Reporting dashboard | Sev 4 | One chart rendering stale data | Cache key missed timezone component | Cache key now includes tz; backfill re-run | Priya Nair | Closed
INC-1044 | 2026-07-18 | Auth service | Sev 2 | Login latency spiked to 8 seconds for 40 minutes | Connection pool exhausted by a slow migration query | Migration moved off-peak; pool alerts added | Sam Whitlock | Action Assigned
INC-1045 | 2026-07-23 | File uploads | Sev 2 | Uploads over 50 MB failing since morning deploy | Proxy body-size limit reset by config rollout | Limit restored; config value pinned in template | Priya Nair | Under Investigation