## Project Kickoff Agenda
Agenda Item | Type | Owner | Minutes | Ends At (min) | Notes and Outcomes
AGENDA |  |  |  |  | 75 minute slot
Why this project, why now | Inform | Dana Whitfield | 10 | 10 | Sponsor speaks, no slides
Scope walkthrough: in and out | Discuss | Lena Fischer | 15 | 25 | The out list matters most
Roles and the RACI | Discuss | Lena Fischer | 10 | 35 | Draft RACI on screen
Timeline and the first milestone | Discuss | Maya Chen | 10 | 45 | Milestone one in four weeks
Risks round: top three from each lead | Discuss | Everyone | 15 | 60 | Lena facilitates and scribes
Decision: sprint one start date | Decide | Lena Fischer | 5 | 65
Working agreements and cadence | Decide | Everyone | 10 | 75 | Standup time, demo day, channel
Total |  |  | 75 |  | Fits the 75 minute slot
DECISIONS AND ACTIONS CAPTURED |  |  |  |  | Filled in during the meeting
Decision: sprint one starts September 14 |  | Lena Fischer |  |  | Agreed by all leads
Action: publish the RACI |  | Lena Fischer |  |  | Before sprint one
Action: seed the risk register |  | Sam Okafor |  |  | Nine risks from the round