## Milestone Rollup
Milestone | Phase | Owner | Baseline Finish | Forecast Finish | Variance (Days) | Status
Requirements sign-off | Design | Clara Boone | 2026-05-15 | 2026-05-15 | 0 | Complete
Solution design approved | Design | Felix Ward | 2026-06-05 | 2026-06-09 | 4 | Complete
Environment provisioning | Build | Felix Ward | 2026-06-19 | 2026-06-19 | 0 | Complete
Data model build complete | Build | Felix Ward | 2026-07-03 | 2026-07-08 | 5 | Complete
Core configuration complete | Build | Nia Campbell | 2026-07-24 | 2026-07-29 | 5 | On Track
Integration development complete | Build | Felix Ward | 2026-08-07 | 2026-08-18 | 11 | At Risk
System test complete | Test | Nia Campbell | 2026-08-28 | 2026-09-08 | 11 | At Risk
UAT complete | Test | Clara Boone | 2026-09-18 | 2026-09-25 | 7 | On Track
Training delivered | Deploy | Nia Campbell | 2026-09-25 | 2026-09-25 | 0 | On Track
Go-live | Deploy | Clara Boone | 2026-10-05 | 2026-10-12 | 7 | At Risk
Hypercare exit | Deploy | Nia Campbell | 2026-10-23 | 2026-10-30 | 7 | On Track
Project closure | Deploy | Clara Boone | 2026-10-30 | 2026-11-06 | 7 | On Track