## Project Task Summary
Task | Owner | Start | Finish | % Complete | Status
Phase 1: Design | Clara Boone | 2026-05-04 | 2026-06-09 | 100 | Complete
Requirements workshops | Clara Boone | 2026-05-04 | 2026-05-15 | 100 | Complete
Process design, 6 workflows | Nia Campbell | 2026-05-18 | 2026-05-29 | 100 | Complete
Solution architecture | Felix Ward | 2026-05-25 | 2026-06-09 | 100 | Complete
Phase 2: Build | Felix Ward | 2026-06-10 | 2026-08-18 | 66 | In Progress
Environment setup | Felix Ward | 2026-06-10 | 2026-06-19 | 100 | Complete
Data model and migrations | Felix Ward | 2026-06-22 | 2026-07-08 | 100 | Complete
Core configuration | Nia Campbell | 2026-07-09 | 2026-07-29 | 45 | In Progress
Integrations (4 interfaces) | Felix Ward | 2026-07-13 | 2026-08-18 | 20 | In Progress
Phase 3: Test | Nia Campbell | 2026-08-19 | 2026-09-25 | 0 | Not Started
System test, 2 cycles | Nia Campbell | 2026-08-19 | 2026-09-08 | 0 | Not Started
UAT with 12 business users | Clara Boone | 2026-09-09 | 2026-09-25 | 0 | Not Started
Performance test | Felix Ward | 2026-09-14 | 2026-09-22 | 0 | Not Started
Phase 4: Deploy | Clara Boone | 2026-09-28 | 2026-11-06 | 0 | Not Started
Training, 3 waves | Nia Campbell | 2026-09-28 | 2026-10-02 | 0 | Not Started
Cutover and go-live | Felix Ward | 2026-10-08 | 2026-10-12 | 0 | Not Started
Hypercare | Nia Campbell | 2026-10-13 | 2026-10-30 | 0 | Not Started
Closure and lessons learned | Clara Boone | 2026-11-02 | 2026-11-06 | 0 | Not Started