## Multi-Project Budget Overview
Project | Owner | Budget ($) | Committed | Actual ($) | % Used | Status | Notes
Website replatform | Dana Whitfield | 84260 | 65600 | 51400 | 61 | On budget | The single-project sheet rolls up here
CRM data cleanup | Marcus Lee | 22000 | 19800 | 14300 | 65 | On budget
Warehouse WMS rollout | Elena Ruiz | 145000 | 151000 | 98200 | 68 | Watch | Committed past budget, change order pending
Mobile app v2 | Ana Torres | 96000 | 88400 | 91700 | 96 | Over | Two sprints left, tracking 8 percent over
Security audit | Noor Haddad | 18500 | 18500 | 17900 | 97 | On budget | Final report invoiced
Office relocation | Jack Morrow | 18700 | 18700 | 18785 | 100 | Over | Closed 85 over, see the simple budget
Brand refresh | Ines Fabri | 32000 | 12000 | 9400 | 29 | On budget | Agency phase two not yet contracted
Total |  | 416460 | 374000 | 301685 | 72