## Project Budget
Line Item | Planned ($) | Committed ($) | Actual ($) | Variance ($) | % Used | Notes
PEOPLE AND CONTRACTORS
Design agency | 12000 | 12000 | 11400 | 600 | 95 | Fixed fee, final invoice in
Contract developers | 36000 | 30000 | 18500 | 17500 | 51 | Two devs, 12 of 20 sprint-weeks billed
Content migration temp | 6500 | 6500 | 6900 | -400 | 106 | Ran 400 over, covered from contingency
SOFTWARE AND INFRASTRUCTURE
CMS licenses | 8400 | 8400 | 8400 | 0 | 100 | Annual license, paid up front
Hosting and CDN | 3600 | 3000 | 1800 | 1800 | 50 | Monthly, half the year committed
Analytics and QA tools | 2400 | 1900 | 1900 | 500 | 79 | Two seats fewer than planned
OTHER DIRECT COSTS
User testing incentives | 1500 | 900 | 900 | 600 | 60 | Two of three rounds run
Training and docs | 2200 | 0 | 0 | 2200 | 0 | Starts after launch
Launch marketing | 4000 | 2500 | 1200 | 2800 | 30 | Ads booked, spend ramping
BUDGET SUMMARY
Direct cost subtotal | 76600 | 65200 | 51000 | 25600 | 67 | Every priced line above
Contingency at 10 percent | 7660 | 400 | 400 | 7260 | 5 | One draw: content migration ran 400 over
Total project budget | 84260 | 65600 | 51400 | 32860 | 61 | Approved ceiling for the project