## Agile Team Charter
Element | Description | Owner | Agreed | Last Reviewed
Product Vision | The fastest way for field crews to log inspections | Ana Torres | TRUE | 2026-07-01
Mission This Quarter | Ship offline mode and cut sync errors in half | Ana Torres | TRUE | 2026-07-01
North-Star Metric | Weekly active inspectors | Ana Torres | TRUE | 2026-07-01
Team | 2 mobile, 2 backend, 1 designer, 1 QA | Ben Carter | TRUE | 2026-07-01
Product Lead | Ana Torres | Ana Torres | TRUE | 2026-07-01
Delivery Lead | Ben Carter | Ben Carter | TRUE | 2026-07-01
Sprint Length | 2 weeks, Wednesday to Tuesday | Ben Carter | TRUE | 2026-07-01
Ceremonies | Daily 9:15 standup, review + retro on close day | Ben Carter | TRUE | 2026-07-01
Definition of Ready | Story sized, acceptance criteria, no open blockers | Yuki Tanaka | TRUE | 2026-07-01
Definition of Done | Code reviewed, tested on device, behind a flag | Yuki Tanaka | TRUE | 2026-07-01
Working Agreement | Core hours 10 to 3, no-meeting Thursdays | Ben Carter | TRUE | 2026-07-01
Working Agreement | PRs reviewed within one business day | Yuki Tanaka | FALSE | 2026-07-08
Escalation Path | Blockers over 1 day go to Ana, then the sponsor | Ana Torres | TRUE | 2026-07-01
Success Criteria | Offline mode at 99 percent sync success by Sept 30 | Ana Torres | FALSE | 2026-07-08