## Charter with Approval Sign-Off
Section | Detail | Approver | Role | Approval Status | Approval Date
Business Case | $95K investment, 14-month payback | Elena Ruiz | Sponsor | Approved | 2026-07-03
Scope Statement | WMS rollout for the Reno and Boise sites | Jack Morrow | Project Manager | Approved | 2026-07-03
Delivery Schedule | Phased cutover, Aug 10 to Nov 20 | Jack Morrow | Project Manager | Approved | 2026-07-03
Budget and Funding | Capital request CR-2214, contingency 12 percent | Grace Lin | Finance Director | Approved | 2026-07-07
Resource Plan | 6 FTE core team plus vendor services | Noor Haddad | PMO Lead | Approved | 2026-07-07
Risk Register | Top 10 risks scored and owned | Noor Haddad | PMO Lead | Approved | 2026-07-07
Data Privacy Review | No customer PII in scope | Mira Sandoval | Legal Counsel | Approved | 2026-07-08
Security Review | Vendor access model and network zoning | Raj Patel | Security Lead | Pending
Vendor Contract | SOW v3 with revised penalty clause | Mira Sandoval | Legal Counsel | Changes Requested
Communication Plan | Weekly steering note plus site briefings | Noor Haddad | PMO Lead | Approved | 2026-07-08
Training Plan | Shift-by-shift floor training in week 10 | Victor Osei | Site Director | Pending
Go-Live Criteria | Inventory accuracy 99.5 percent in dress rehearsal | Victor Osei | Site Director | Pending
Sign-Off Progress | 8 of 12 sections approved |  | Auto-count