## Classic Project Charter
Section | Detail | Owner | Status | Last Updated
Project Name | Atlas CRM Migration | Marcus Lee | Approved | 2026-07-06
Project Sponsor | Dana Whitfield, VP Operations | Dana Whitfield | Approved | 2026-07-06
Project Manager | Marcus Lee | Marcus Lee | Approved | 2026-07-06
Business Case | Legacy CRM contract ends Q4; move saves $85K a year | Dana Whitfield | Approved | 2026-07-06
Problem Statement | Sales and support work from separate customer records | Marcus Lee | Approved | 2026-07-02
Objective 1 | Migrate 40,000 customer records with zero data loss | Ines Fabri | Approved | 2026-07-02
Objective 2 | Cut average case handling time by 20 percent | Sarah Kim | In Review | 2026-07-08
Objective 3 | Retire the legacy system by November 30 | Tom Okonkwo | In Review | 2026-07-08
In Scope | Sales, support, and billing workflows for NA region | Marcus Lee | Approved | 2026-07-02
Out of Scope | EMEA rollout and the custom mobile app | Marcus Lee | Approved | 2026-07-02
Key Deliverable | Cleansed, deduplicated customer master data | Ines Fabri | In Review | 2026-07-09
Key Deliverable | Team training plan and playbooks | Sarah Kim | Draft | 2026-07-09
Milestone | Data audit complete: Aug 14 | Ines Fabri | Approved | 2026-07-02
Milestone | Pilot go-live: Oct 2 | Marcus Lee | In Review | 2026-07-08
Budget | $120K: licenses 48, services 52, training 20 | Dana Whitfield | In Review | 2026-07-08
Key Risk | Legacy data quality may delay the pilot | Ines Fabri | Draft | 2026-07-09
Assumption | Vendor sandbox available from July 20 | Tom Okonkwo | Draft | 2026-07-09
Success Criteria | 100 percent of active accounts migrated and verified | Dana Whitfield | In Review | 2026-07-08