## One-Page Executive Charter
Item | Summary | Owner | Approved
Purpose | Automate pallet picking at the Reno warehouse | Elena Ruiz | TRUE
Opportunity | Cut per-order handling cost by 31 percent | Elena Ruiz | TRUE
Goal | Pilot line live by September 15 | Jack Morrow | TRUE
Scope | One pick line, 4 robots, existing WMS integration | Jack Morrow | TRUE
Out of Scope | Packing stations and outbound sortation | Jack Morrow | TRUE
Timeline | 12 weeks: design 3, install 5, ramp 4 | Jack Morrow | FALSE
Budget | $410K capital, $60K contingency | Elena Ruiz | FALSE
Team | PM, 2 engineers, vendor crew, shift lead | Noor Haddad | TRUE
Top Risk | Robot delivery slips past week 6 | Jack Morrow | FALSE
Decision Needed | Approve vendor SOW by July 18 | Elena Ruiz | FALSE
Success Measure | 220 picks per hour sustained for 2 weeks | Noor Haddad | FALSE
Next Milestone | Design review: July 24 | Jack Morrow | FALSE