## Multi-Project Tracker
Project | Task | Owner | Due Date | Priority | Status
Website Refresh | Approve revised homepage design | Maya Chen | 2026-07-14 | High | In Progress
Website Refresh | Content freeze for migration | Rosa Vega | 2026-07-21 | Medium | Not Started
Website Refresh | Launch checklist review | Liam Doyle | 2026-08-06 | Medium | Not Started
Warehouse Move | Sign lease amendment | Paula Brandt | 2026-07-11 | High | Blocked
Warehouse Move | Racking vendor site survey | Omar Reyes | 2026-07-16 | High | In Progress
Warehouse Move | IT cutover plan for WMS | Dev Sharma | 2026-07-23 | High | In Progress
Warehouse Move | Move-day labor schedule | Kate Muir | 2026-07-30 | Medium | Not Started
Warehouse Move | Update insurance certificates | Grace Lin | 2026-07-18 | Low | Complete
ERP Phase 2 | UAT scenario sign-off | Lena Voss | 2026-07-15 | High | In Progress
ERP Phase 2 | Train warehouse leads (2 sessions) | Kate Muir | 2026-07-24 | Medium | Not Started
ERP Phase 2 | Cutover rehearsal | Dev Sharma | 2026-07-29 | High | Not Started
ERP Phase 2 | Data reconciliation report | Lena Voss | 2026-08-03 | Medium | Not Started
Website Refresh | SEO redirect validation | Rosa Vega | 2026-08-11 | Medium | Not Started
Warehouse Move | Certificate of occupancy walkthrough | Omar Reyes | 2026-08-13 | High | Not Started
ERP Phase 2 | Go/no-go steering review | Paula Brandt | 2026-08-07 | High | Not Started
Website Refresh | Post-launch metrics report | Maya Chen | 2026-08-25 | Low | Not Started
Warehouse Move | Old site decommission | Omar Reyes | 2026-08-27 | Low | Not Started
ERP Phase 2 | Hypercare rota (2 weeks) | Dev Sharma | 2026-08-17 | Medium | Not Started