## Simple Task Tracker
Task | Owner | Due Date | Status | Notes
Finalize sitemap and page list | Maya Chen | 2026-07-03 | Complete | Signed off July 2
Write homepage copy | Maya Chen | 2026-07-10 | In Progress | Second draft in review
Design system and component library | Rosa Vega | 2026-07-08 | Complete
Homepage design | Rosa Vega | 2026-07-15 | In Progress
Interior page templates (5) | Rosa Vega | 2026-07-22 | Not Started
Product photography | Maya Chen | 2026-07-17 | Blocked | Waiting on sample units from client
CMS setup and content model | Liam Doyle | 2026-07-14 | In Progress
Build homepage | Liam Doyle | 2026-07-21 | Not Started
Build interior templates | Liam Doyle | 2026-07-29 | Not Started
Migrate blog content (64 posts) | Rosa Vega | 2026-07-31 | Not Started | Script drafted
Contact form and CRM integration | Liam Doyle | 2026-07-28 | Not Started
Redirect map for old URLs | Rosa Vega | 2026-08-04 | Not Started | 231 URLs inventoried
Analytics and event tracking | Liam Doyle | 2026-08-05 | Not Started
Cross-browser and mobile QA | Maya Chen | 2026-08-07 | Not Started
Accessibility pass | Rosa Vega | 2026-08-10 | Not Started
Launch and DNS cutover | Liam Doyle | 2026-08-12 | Not Started | Tuesday morning window