## Task Tracker with Timeline Math
Task | Owner | Start | Due Date | % Complete | Days Remaining | Status
Kickoff and requirements workshop | Ana Torres | 2026-06-22 | 2026-06-24 | 100 | 0 | Complete
Field data model design | Ben Carter | 2026-06-25 | 2026-07-02 | 100 | 0 | Complete
Offline sync engine spike | Ben Carter | 2026-07-01 | 2026-07-08 | 100 | 0 | Complete
Inspection form builder | Yuki Tanaka | 2026-07-06 | 2026-07-17 | 65 | 8 | In Progress
Photo capture and annotation | Ben Carter | 2026-07-09 | 2026-07-21 | 30 | 12 | In Progress
Sync conflict resolution rules | Ana Torres | 2026-07-13 | 2026-07-24 | 10 | 15 | In Progress
Report PDF generation | Yuki Tanaka | 2026-07-20 | 2026-07-30 | 0 | 21 | Not Started
Crew scheduling screen | Ben Carter | 2026-07-22 | 2026-08-04 | 0 | 26 | Not Started
Push notification service | Yuki Tanaka | 2026-07-27 | 2026-08-06 | 0 | 28 | Not Started
Beta build to 5 pilot crews | Ana Torres | 2026-08-05 | 2026-08-11 | 0 | 33 | Not Started
Pilot feedback triage | Ana Torres | 2026-08-12 | 2026-08-19 | 0 | 41 | Not Started
Performance and battery pass | Ben Carter | 2026-08-17 | 2026-08-25 | 0 | 47 | Not Started
App store submission | Yuki Tanaka | 2026-08-26 | 2026-08-28 | 0 | 50 | Not Started
Launch review | Ana Torres | 2026-08-31 | 2026-08-31 | 0 | 53 | Not Started