## Program-Level RAID Log
Workstream | Type | Summary | Owner | Escalation | Status | Due Date
Platform | Risk | Core API vendor roadmap slips a quarter | Dev Sharma | Executive | Open | 2026-07-24
Data Migration | Risk | Legacy item master fails validation at 12 percent | Lena Voss | Program | Mitigating | 2026-07-31
Change Management | Risk | Union consultation window not yet booked | Kate Muir | Executive | Open | 2026-07-17
Site Operations | Risk | Peak season overlaps wave 2 cutover | Omar Reyes | Program | Mitigating | 2026-08-14
Platform | Dependency | SSO federation from corporate IT | Omar Reyes | Program | Open | 2026-08-07
Data Migration | Dependency | Finance close calendar locks freeze dates | Grace Lin | Project | Open | 2026-07-31
Change Management | Issue | Training rooms unavailable at Boise site | Kate Muir | Project | Mitigating | 2026-07-24
Platform | Issue | Test environment refresh broken 4 days | Dev Sharma | Project | Mitigating | 2026-07-15
Site Operations | Issue | Wave 1 site missing 2 supervisor hires | Paula Brandt | Program | Open | 2026-08-21
Data Migration | Assumption | Vendor conversion scripts reusable across sites | Lena Voss | Project | Open | 2026-08-07
Change Management | Assumption | Managers can absorb 6 hours of training | Kate Muir | Project | Open | 2026-08-14
Platform | Assumption | No major version upgrade during program | Dev Sharma | Program | Open | 2026-09-04
Site Operations | Dependency | Racking install complete before go-live | Omar Reyes | Program | Mitigating | 2026-09-11
Data Migration | Issue | Duplicate supplier records across regions | Lena Voss | Project | Mitigating | 2026-08-07
Platform | Risk | Interface volume 3x higher than sized | Dev Sharma | Program | Open | 2026-08-28