## RAID Log with Risk Scoring
Type | Item | Probability (1-5) | Impact (1-5) | Risk Score | Severity | Owner
Risk | Data migration misses the freeze window | 4 | 5 | 20 | Critical | Paula Brandt
Risk | Key integration partner slips their API date | 3 | 4 | 12 | High | Dev Sharma
Risk | Warehouse staff not trained before cutover | 3 | 5 | 15 | Critical | Kate Muir
Risk | Budget overrun on data cleansing services | 2 | 3 | 6 | Medium | Paula Brandt
Risk | Duplicate vendor records corrupt purchase orders | 2 | 5 | 10 | High | Lena Voss
Risk | Peak-season change freeze compresses testing | 4 | 3 | 12 | High | Dev Sharma
Assumption | Finance team available for UAT in September |  |  |  |  | Kate Muir
Assumption | Current chart of accounts maps 1 to 1 |  |  |  |  | Lena Voss
Assumption | Vendor test environment mirrors production |  |  |  |  | Dev Sharma
Issue | Sandbox refresh has been down since Monday |  |  |  |  | Dev Sharma
Issue | Item master extract missing 3 warehouse codes |  |  |  |  | Lena Voss
Issue | Two workstream leads double-booked in August |  |  |  |  | Paula Brandt
Issue | Legacy report inventory still incomplete |  |  |  |  | Kate Muir
Dependency | SSO group setup by corporate IT |  |  |  |  | Omar Reyes
Dependency | Network upgrade at the Fresno DC |  |  |  |  | Omar Reyes
Dependency | Signed data processing addendum from vendor |  |  |  |  | Paula Brandt