## RAID Plus Decisions Log
Ref | Category | Summary | Owner | Date Raised | Status | Outcome / Notes
D-01 | Decision | Single-region hosting for launch | Paula Brandt | 2026-06-04 | Closed | Approved at June 4 steering; revisit at 10K users
R-01 | Risk | Payment provider sandbox instability | Dev Sharma | 2026-06-05 | In Progress | Second provider in evaluation
A-01 | Assumption | Support handles launch volume with 4 agents | Kate Muir | 2026-06-05 | Open | Validate against beta ticket rates
I-01 | Issue | Staging data anonymization incomplete | Lena Voss | 2026-06-09 | In Progress | Masking job in review
D-02 | Decision | Launch pricing set at $29 and $79 tiers | Paula Brandt | 2026-06-11 | Closed | Signed off by sponsor June 11
DP-01 | Dependency | App store review turnaround | Omar Reyes | 2026-06-12 | Open | Submit 3 weeks before launch day
R-02 | Risk | Beta churn masks activation problems | Kate Muir | 2026-06-16 | Open | Cohort dashboard due June 27
I-02 | Issue | Email domain flagged by one B2B filter | Omar Reyes | 2026-06-18 | Closed | Remediated; warmed backup domain
D-03 | Decision | Postpone SSO to fast-follow release | Paula Brandt | 2026-06-20 | Closed | Two enterprise deals accept timeline
A-02 | Assumption | No schema changes needed for EU data | Lena Voss | 2026-06-23 | Open | Legal review returns July 15
R-03 | Risk | Key engineer on leave over cutover week | Paula Brandt | 2026-06-25 | In Progress | Cross-training started
DP-02 | Dependency | Marketing site refresh ships first | Kate Muir | 2026-06-26 | In Progress | Shared launch checklist
I-03 | Issue | Load test found N+1 on the orders page | Dev Sharma | 2026-06-30 | Closed | Fixed; p95 down 380ms
D-04 | Decision | Beta feedback triaged weekly, not daily | Kate Muir | 2026-07-01 | Closed | Agreed in July 1 standup
R-04 | Risk | Analytics vendor contract lapses mid-quarter | Grace Lin | 2026-07-02 | Open | Renewal quote requested
A-03 | Assumption | Current CDN plan covers launch traffic | Omar Reyes | 2026-07-06 | Open | Confirm burst pricing
DP-03 | Dependency | Final security review before GA | Raj Patel | 2026-07-07 | Open | Booked for August 3 week
D-05 | Decision | GA date confirmed for September 9 | Paula Brandt | 2026-07-08 | Closed | All workstreams green at July 8 review