## Simple Risk Register
Risk | Likelihood | Impact | Mitigation | Owner | Status | Review Date
Copy deck late from the brand agency | High | Medium | Lock deck scope; weekly copy review | Maya Chen | Open | 2026-07-17
Holiday freeze blocks the launch window | Medium | High | Target Nov 12; fallback Jan 8 | Liam Doyle | Open | 2026-07-17
Checkout redesign hurts conversion | Medium | High | A/B test on 20 percent of traffic first | Rosa Vega | Open | 2026-07-24
CMS plugin unsupported on new stack | Medium | Medium | Spike replacement in sprint 2 | Liam Doyle | Monitoring | 2026-07-24
Photography reshoot runs over budget | Low | Medium | Reuse spring shoot; cap reshoot at 1 day | Maya Chen | Monitoring | 2026-07-31
SEO rankings dip after URL changes | High | High | Redirect map plus staged rollout | Rosa Vega | Open | 2026-07-17
Accessibility audit finds late blockers | Medium | High | Audit at 60 percent build, not at the end | Liam Doyle | Open | 2026-07-31
Stakeholder review cycle stalls sign-off | Medium | Medium | Single approver per page, 48-hour SLA | Maya Chen | Monitoring | 2026-07-24
Analytics tagging breaks in migration | Medium | Medium | Tag plan owned by data; QA checklist | Rosa Vega | Open | 2026-07-31
Third-party reviews widget slows pages | Low | Medium | Lazy-load and set a perf budget | Liam Doyle | Monitoring | 2026-08-07
Legal review of claims copy delays pages | Low | High | Pre-clear claims list with counsel now | Maya Chen | Open | 2026-07-17
Traffic spike overwhelms staging tests | Low | Low | Load test at 3x forecast before launch | Rosa Vega | Closed | 2026-07-03