## Release Status Rollup
Workstream | Owner | Items | Done | % Complete | Risk | Status
Core app changes | Lena Ivanov | 14 | 11 | 79 | Low | On Track
Mobile release | Kat Weber | 9 | 4 | 44 | Medium | At Risk
Data migrations | Lena Ivanov | 5 | 5 | 100 | Low | On Track
QA regression | Owen Diaz | 22 | 15 | 68 | Medium | On Track
Docs and release notes | Maya Okafor | 6 | 3 | 50 | Low | On Track
Support readiness | Priya Shah | 4 | 1 | 25 | High | Blocked
Marketing announcement | Rui Costa | 5 | 2 | 40 | Medium | At Risk
Infrastructure and rollback | Kat Weber | 7 | 6 | 86 | Low | On Track
Release total |  | 72 | 47 | 65