## Sprint Release Tracker
Release | Target Date | Days Out | Owner | Scope Frozen | Risk | Status
v2.3 Alerts and digests | 2026-08-20 | 0 | Lena Ivanov | TRUE | Low | Released
v2.3.1 Hotfix, Safari charts | 2026-08-24 | 0 | Kat Weber | TRUE | Low | Released
v2.4 SSO and audit logs | 2026-09-10 | 13 | Lena Ivanov | TRUE | Medium | In Progress
Mobile 5.1, sign-in fixes | 2026-09-12 | 15 | Kat Weber | TRUE | Medium | In Progress
v2.4.1 Scheduled reports | 2026-09-24 | 27 | Lena Ivanov | FALSE | Low | In Progress
Mobile 5.2, widgets beta | 2026-10-08 | 41 | Kat Weber | FALSE | Medium | Planning
v2.5 Guest links | 2026-10-15 | 48 | Lena Ivanov | FALSE | Medium | Planning
Data platform 1.0, warehouse sync | 2026-10-29 | 62 | Lena Ivanov | FALSE | High | Planning
v2.5.1 Custom fields | 2026-11-12 | 76 | Maya Okafor | FALSE | Medium | Planning
v2.6 Usage analytics | 2026-11-25 | 89 | Rui Costa | FALSE | Low | Planning
Holiday code freeze window | 2026-12-18 | 112 | Lena Ivanov | TRUE | Low | Planning
v2.7 Forecasting beta | 2027-01-14 | 139 | Maya Okafor | FALSE | High | Planning