## Employee Resource Plan
Person | Role | Portal % | Mobile % | Migration % | BAU % | Allocated % | Available % | Load
Maya Chen | Tech lead | 60 | 30 | 20 | 10 | 120 | -20 | Overallocated
Jonas Petersen | Backend engineer | 50 | 0 | 40 | 10 | 100 | 0 | Full
Priya Sharma | Frontend engineer | 70 | 0 | 0 | 15 | 85 | 15 | Has capacity
Diego Alvarez | Designer | 40 | 45 | 0 | 10 | 95 | 5 | Full
Hannah Roth | QA engineer | 30 | 30 | 30 | 10 | 100 | 0 | Full
Sam Okafor | Data engineer | 0 | 0 | 80 | 15 | 95 | 5 | Full
Lena Fischer | Project manager | 35 | 25 | 25 | 20 | 105 | -5 | Overallocated
Tomas Silva | Backend engineer | 0 | 55 | 20 | 10 | 85 | 15 | Has capacity
Aisha Khan | Frontend engineer | 0 | 60 | 0 | 10 | 70 | 30 | Has capacity
Rob Nguyen | DevOps engineer | 20 | 15 | 25 | 30 | 90 | 10 | Full
Team total | 100 points = one full-time person | 305 | 260 | 240 | 140 | 945