## Project Staffing Plan
Role | Needed | Assigned To | Committed | Gap | Status | Start By | Notes
Tech lead | 0.5 | Maya Chen | 0.5 | 0 | Filled | 2026-09-07 | Shared with the Mobile App
Backend engineer | 2 | Jonas Petersen | 1 | 1 | Partial | 2026-09-07 | Second seat open, interviews running
Frontend engineer | 1.5 | Priya Sharma | 1 | 0.5 | Partial | 2026-09-14 | Half a seat still unassigned
Designer | 0.5 | Diego Alvarez | 0.5 | 0 | Filled | 2026-09-07
QA engineer | 1 | Hannah Roth | 0.75 | 0.25 | Partial | 2026-09-21 | Hannah frees up fully in October
Data engineer | 1 |  | 0 | 1 | Open | 2026-09-14 | Contractor shortlist due Sep 12
DevOps engineer | 0.25 | Rob Nguyen | 0.25 | 0 | Filled | 2026-09-07
Project manager | 0.5 | Lena Fischer | 0.5 | 0 | Filled | 2026-09-07
Technical writer | 0.25 |  | 0 | 0.25 | Open | 2026-10-05 | Needed for the launch docs
Total | 7.5 |  | 4.5 | 3