## Resource Allocation by Hours
Person | Project | Assignment | Hours per Week | Start | End | Hours Free (of 32)
ASSIGNMENTS | One row per person per project, hours per week
Maya Chen | Portal Rebuild | API design and reviews | 16 | 2026-09-07 | 2026-10-30
Maya Chen | Mobile App | Architecture reviews | 10 | 2026-09-07 | 2026-11-27
Maya Chen | Data Migration | Cutover plan | 8 | 2026-09-14 | 2026-10-16
Priya Sharma | Portal Rebuild | Portal UI build | 24 | 2026-09-07 | 2026-11-13
Priya Sharma | BAU and Support | Support rotation | 4 | 2026-09-07 | 2026-12-18
Sam Okafor | Data Migration | Pipeline build and dry runs | 26 | 2026-09-07 | 2026-11-06
Sam Okafor | BAU and Support | Reporting dashboards | 6 | 2026-09-07 | 2026-12-18
Aisha Khan | Mobile App | Feature screens | 20 | 2026-09-14 | 2026-11-27
Lena Fischer | Portal Rebuild | Coordination and standups | 12 | 2026-09-07 | 2026-11-13
Lena Fischer | Mobile App | Coordination | 8 | 2026-09-07 | 2026-11-27
Lena Fischer | Data Migration | Coordination | 8 | 2026-09-14 | 2026-11-06
Lena Fischer | BAU and Support | Intake triage | 6 | 2026-09-07 | 2026-12-18
WEEKLY TOTALS BY PERSON | Against 32 project hours of a 40 hour week
Maya Chen | All projects | Total across assignments | 34 |  |  | -2
Priya Sharma | All projects | Total across assignments | 28 |  |  | 4
Sam Okafor | All projects | Total across assignments | 32 |  |  | 0
Aisha Khan | All projects | Total across assignments | 20 |  |  | 12
Lena Fischer | All projects | Total across assignments | 34 |  |  | -2