## Construction Risk Register
Risk | Phase | Probability | Impact | Score | Rating | Control Measure | Owner | Review By | Status
Wet weather stops the slab pour beyond the float | Sitework | 4 | 4 | 16 | Red | Two pour dates held; covers and pumps on standby | Hank Delgado | 2026-08-07 | Mitigating
Rock encountered below the footing line | Sitework | 3 | 5 | 15 | Red | Bore logs reviewed; breaker priced as a provisional sum | Rosa Milani | 2026-08-04 | Open
Roof truss delivery slips past the frame date | Structure | 3 | 5 | 15 | Red | Order released early; second supplier prequalified | Hank Delgado | 2026-08-12 | Mitigating
Electrical rough-in fails first inspection | MEP | 3 | 4 | 12 | Amber | Pre-inspection walk with the sparky before booking | Rosa Milani | 2026-08-19 | Open
Fall from height during the frame stage | Structure | 2 | 5 | 10 | Amber | Edge protection signed off daily; harness audit weekly | Tyrell Banks | 2026-08-05 | Mitigating
Utility connection date moves and holds up closeout | Closeout | 3 | 4 | 12 | Amber | Application lodged at permit stage; weekly chase logged | Rosa Milani | 2026-09-02 | Open
Tile and fixture selections not confirmed by the owner | Finishes | 4 | 3 | 12 | Amber | Selections deadline in the contract; reminders at 30 and 14 days | Rosa Milani | 2026-08-26 | Mitigating
Concrete price rises before the second pour | Structure | 3 | 3 | 9 | Amber | Quantity locked with the supplier for 90 days | Hank Delgado | 2026-08-14 | Open
Framing crew pulled to another job | Structure | 2 | 4 | 8 | Amber | Written crew commitment; backup subbie on call | Hank Delgado | 2026-08-21 | Open
Silt runoff breaches the site water controls | Sitework | 2 | 4 | 8 | Amber | Silt fence checked after every rain event and logged | Tyrell Banks | 2026-08-08 | Mitigating
Owner change orders stack up and stall the schedule | Finishes | 3 | 2 | 6 | Green | Every change priced and signed before work starts | Rosa Milani | 2026-09-09 | Open
Punch list drags past the handover date | Closeout | 2 | 3 | 6 | Green | Trade-by-trade sign-off two weeks before handover | Hank Delgado | 2026-09-16 | Open