## Program Risk Register
ID | Risk | Workstream | Inherent Score | Mitigation | Residual Score | Owner | Escalated | Review By | Status
R-001 | Core platform cutover exceeds the agreed outage window | Platform | 20 | Rehearsed cutover twice against a full-size copy | 8 | Ken Ishida | TRUE | 2026-08-06 | Mitigating
R-002 | Customer data migration corrupts historical balances | Data | 20 | Two-pass migration with a reconciliation report per batch | 6 | Marta Lindqvist | TRUE | 2026-08-13 | Mitigating
R-003 | Regulatory reporting change lands mid-program | Commercial | 15 | Requirements watch with a monthly read from counsel | 12 | Adaora Nwosu | TRUE | 2026-08-20 | Open
R-004 | Two workstreams depend on the same integration team | Platform | 16 | Shared team capacity booked and published per sprint | 8 | Ken Ishida | FALSE | 2026-08-27 | Mitigating
R-005 | Operations cannot absorb the new process at go-live | Operations | 15 | Phased regional rollout with a hypercare desk | 9 | Adaora Nwosu | FALSE | 2026-09-03 | Open
R-006 | Vendor support contract expires before hypercare ends | Commercial | 12 | Extension negotiated to 90 days past the final wave | 4 | Adaora Nwosu | FALSE | 2026-08-10 | Closed
R-007 | Reference data ownership is unassigned across workstreams | Data | 12 | Named data owner per domain with a monthly review | 6 | Marta Lindqvist | FALSE | 2026-09-10 | Mitigating
R-008 | Program loses two senior engineers to another program | People | 12 | Retention plan agreed; knowledge documented weekly | 9 | Ken Ishida | FALSE | 2026-09-17 | Open
R-009 | Benefit case slips because adoption is slower than modelled | Commercial | 12 | Adoption tracked weekly with a named regional sponsor | 8 | Adaora Nwosu | FALSE | 2026-09-24 | Open
R-010 | Test environments unavailable during the peak test window | Platform | 10 | Environment calendar owned by the program, booked 6 weeks out | 4 | Ken Ishida | FALSE | 2026-08-17 | Closed
R-011 | Training completion lags the wave-two cutover | People | 9 | Completion reported per store weekly; cutover gated on it | 6 | Marta Lindqvist | FALSE | 2026-09-07 | Open
R-012 | Third-party reporting feed changes format without notice | Data | 9 | Schema check on ingest with an alert to the data owner | 3 | Marta Lindqvist | FALSE | 2026-08-24 | Mitigating