## Scored Risk Register
Risk | Category | Probability | Impact | Score | Rating | Owner | Response Strategy | Review By | Status
Store broadband upgrades slip behind the rollout schedule | Delivery | 4 | 5 | 20 | Red | Wes Ackerman | Mitigate | 2026-08-14 | Mitigating
Card terminal firmware fails certification on first pass | Technical | 3 | 5 | 15 | Red | Tomas Bergstrom | Mitigate | 2026-08-07 | Open
Peak trading freeze compresses the pilot window | Delivery | 4 | 4 | 16 | Red | Nadia Farouk | Avoid | 2026-08-21 | Mitigating
Legacy price file does not map cleanly to the new schema | Technical | 3 | 4 | 12 | Amber | Tomas Bergstrom | Mitigate | 2026-08-05 | Mitigating
Store managers under-trained before their cutover night | People | 3 | 4 | 12 | Amber | Joy Okafor | Mitigate | 2026-08-28 | Open
Vendor day-one support cover thinner than contracted | Commercial | 2 | 4 | 8 | Amber | Nadia Farouk | Transfer | 2026-09-04 | Open
Hardware shipment held in customs past the pilot date | Delivery | 2 | 4 | 8 | Amber | Wes Ackerman | Mitigate | 2026-08-18 | Open
Offline mode drops transactions when the line flaps | Technical | 2 | 5 | 10 | Amber | Tomas Bergstrom | Mitigate | 2026-08-11 | Mitigating
Rollout budget overruns on out-of-hours engineer time | Commercial | 3 | 3 | 9 | Amber | Nadia Farouk | Accept | 2026-09-11 | Open
Two regional leads booked on leave in the cutover month | People | 3 | 2 | 6 | Green | Joy Okafor | Accept | 2026-09-18 | Open
Loyalty integration partner slips their API date | Technical | 2 | 3 | 6 | Green | Tomas Bergstrom | Mitigate | 2026-08-25 | Mitigating
Signage and till furniture arrive after the store opens | Delivery | 2 | 2 | 4 | Green | Wes Ackerman | Accept | 2026-09-01 | Closed