## Simple Risk Register
Risk | Likelihood | Impact | Mitigation | Owner | Review By | Status
New lease not signed before the current one ends | Medium | High | Hold a 30-day holdover option with the current landlord | Ellie Nash | 2026-08-10 | Mitigating
Fit-out overruns the two-week shutdown window | High | High | Stage the fit-out by zone; studio can run from zone A | Robert Kim | 2026-08-17 | Open
Fiber install at the new site takes longer than quoted | High | Medium | Order the line now; keep 4G failover for the first month | Robert Kim | 2026-08-03 | Mitigating
Client shoot scheduled inside the move week | Medium | High | Move the shoot or book an external studio day | Ellie Nash | 2026-08-03 | Open
Equipment damaged in transit | Low | High | Specialist crate for camera and lighting; insured in transit | Robert Kim | 2026-08-24 | Open
Parking permit for the removal truck refused | Medium | Medium | Apply six weeks out; fallback loading bay on the side street | Ellie Nash | 2026-08-10 | Mitigating
Team commute gets materially worse for two people | Medium | Medium | Agreed two remote days for the affected pair | Ellie Nash | 2026-09-07 | Closed
Move cost overruns the agreed budget | Medium | Medium | Fixed-price removal quote; 10 percent contingency held | Robert Kim | 2026-08-31 | Open
Post redirect misses invoices during the changeover | Low | Medium | 12-month redirect plus direct notice to the top 20 clients | Ellie Nash | 2026-08-17 | Closed
Old site fails its dilapidations inspection | Low | Medium | Pre-inspection with the agent; make good before handback | Robert Kim | 2026-09-14 | Open