## Roofing Estimate
Item | Detail | Qty | Unit | Unit Cost ($) | Type | Line Total ($)
MEASUREMENTS | Measure once, then every price below hangs off these five rows
Roof footprint | House footprint plus 12 inch overhangs, from the site measure | 1960 | sq ft
Pitch factor | 6/12 pitch. See the pitch table on the page for other slopes | 1.118 | factor
Roof area | Footprint times pitch factor | 2191 | sq ft
Roof squares | Roof area divided by 100 | 21.9 | squares
Squares to order | Plus 10 percent waste for a gable roof, rounded up to whole squares | 25 | squares
TEAR-OFF, DISPOSAL AND FEES
Tear-off, one layer | Crew of four strips 21.9 squares and checks the deck | 22 | crew-hours | 65 | Labor | 1430
Dumpster and disposal | 20 yard container, one pull, about 3 tons of shingles | 1 | dumpster | 525 | Disposal and Fees | 525
Permit and inspection | City reroof permit with final inspection | 1 | permit | 265 | Disposal and Fees | 265
MATERIALS
Architectural shingles | 25 squares to order, 3 bundles per square | 25 | squares | 122 | Materials | 3050
Synthetic underlayment | 10-square rolls across the full deck | 3 | rolls | 95 | Materials | 285
Ice and water shield | Eaves and both valleys, 2-square rolls | 4 | rolls | 110 | Materials | 440
Drip edge | 10 ft sticks for 236 lineal ft of eaves and rakes | 24 | pieces | 10.5 | Materials | 252
Starter strip | Eaves and rakes | 4 | bundles | 55 | Materials | 220
Ridge cap shingles | 46 lineal ft of ridge | 3 | bundles | 68 | Materials | 204
Ridge vent | Shingle-over vent along the full ridge | 40 | lineal ft | 8.5 | Materials | 340
Flashing | Chimney kit, step flashing and three pipe boots | 1 | lot | 385 | Materials | 385
Fasteners and sealant | Coil nails, cap nails and sealant | 1 | lot | 235 | Materials | 235
LABOR
Install labor | Crew of four, 2 crew-hours per square over 22 squares | 44 | crew-hours | 72 | Labor | 3168
Detail labor | Lead installer on flashing and penetrations | 8 | crew-hours | 84 | Labor | 672
Protection and cleanup | Tarps, magnet sweep and the final walk | 6 | crew-hours | 62 | Labor | 372
ESTIMATE SUMMARY
Materials | Everything on the truck |  |  |  |  | 5411
Labor | Tear-off, install, detail and cleanup |  |  |  |  | 5642
Disposal and fees | Dumpster and permit |  |  |  |  | 790
Direct cost subtotal | Every priced line above |  |  |  |  | 11843
Overhead at 10 percent | Insurance, trucks, office and supervision |  |  |  |  | 1184
Margin at 20 percent of price | Figured on the price, not the cost. The page walks through why |  |  |  |  | 3257
Subtotal | Direct costs plus overhead plus margin |  |  |  |  | 16284
Sales tax at 6.5 percent | Check how your state taxes labor on reroofs |  |  |  |  | 1058
Total | Good for 30 days from the estimate date |  |  |  |  | 17342
CUSTOMER SUMMARY | The block the homeowner signs
Price per square | Total divided by roof squares |  |  |  |  | 792
Deposit at signing, 30 percent | Due with the signed estimate |  |  |  |  | 5203
Balance on completion | Due after the final walk and magnet sweep |  |  |  |  | 12139