## Construction Scope of Work
Ref | Trade | Description of Work | Inclusion | Notes
1.01 | Sitework | Demolition of existing slab and haul-off | Included
1.02 | Sitework | Rough and finish grading per C-201 | Included
1.03 | Sitework | Landscape and irrigation | By Others | Owner's landscape contract
2.01 | Concrete | Foundations, piers, and grade beams | Included
2.02 | Concrete | Slab on grade with vapor barrier | Included
2.03 | Concrete | Decorative site flatwork | Excluded | Available as alternate 3
3.01 | Framing | Structural framing per S-sheets | Included
3.02 | Framing | Blocking for owner equipment | Included | Locations per final equipment plan
4.01 | Roofing | TPO roof system, 20-year warranty | Included
4.02 | Roofing | Solar-ready conduit stubs | Included | Per detail 7/A-501
5.01 | MEP | HVAC complete per M-sheets | Included
5.02 | MEP | Electrical service and distribution | Included
5.03 | MEP | Low-voltage cabling and AV | By Others | Owner IT vendor; conduit by GC
5.04 | MEP | Kitchen equipment hookups | Included | Equipment supplied by owner
6.01 | Finishes | Drywall, paint, flooring, ceilings per finish schedule | Included
6.02 | Finishes | Furniture, fixtures, and equipment | Excluded | FF&E under separate owner contract