## Consulting Scope of Work
Section | Detail | Owner | Status
Engagement | Operations assessment and improvement roadmap | Evan Calder | Approved
Client | Northgate Foods, distribution division | Paula Brandt | Approved
Consultant | Calder Group LLC | Evan Calder | Approved
Background | Order error rates doubled since the second DC opened; leadership wants root causes and a costed fix plan | Evan Calder | Approved
Objective 1 | Quantify error sources across intake, picking, and shipping | Nikki Tran | Approved
Objective 2 | Deliver a prioritized improvement roadmap with owner, cost, and payback per initiative | Evan Calder | Approved
In Scope | Both distribution centers, order-to-ship process, WMS configuration review | Evan Calder | Approved
Out of Scope | Transportation carriers, procurement, retail store operations | Evan Calder | Approved
Approach | 3 phases: diagnose (weeks 1-3), design (weeks 4-6), roadmap and readout (weeks 7-8) | Nikki Tran | Approved
Deliverable 1 | Error-source baseline report with pareto by process step | Nikki Tran | In Review
Deliverable 2 | Future-state process designs for the top 5 error sources | Nikki Tran | Draft
Deliverable 3 | Costed improvement roadmap and executive readout | Evan Calder | Draft
Timeline | 8 weeks from kickoff; kickoff July 20, readout September 11 | Evan Calder | Approved
Fees | Fixed fee $86,000, invoiced 40/30/30 at phase completion | Evan Calder | Approved
Expenses | Travel at cost, capped at $6,000, pre-approved weekly | Nikki Tran | Approved
Assumptions | Client provides WMS read access, 6 SME interviews per week, and a named decision-maker per workstream | Evan Calder | Approved
Change Control | Scope changes priced and countersigned before work proceeds | Evan Calder | Approved
Acceptance | Each deliverable reviewed within 5 business days; silence is acceptance | Paula Brandt | In Review