## SOW Deliverables and Acceptance
Deliverable | Milestone | Due Date | Acceptance Criteria | Status | Accepted Date
Project kickoff deck | M1: Kickoff | 2026-07-20 | Approach, staffing, and calendar confirmed in writing | Accepted | 2026-07-21
Data access and tooling setup | M1: Kickoff | 2026-07-24 | Read access verified for WMS and order data | Accepted | 2026-07-24
Error-source baseline report | M2: Diagnose | 2026-08-07 | Pareto covers 95 percent of errors, validated by ops leads | Submitted
SME interview synthesis | M2: Diagnose | 2026-08-07 | 12 interviews complete, findings traceable to transcripts | Submitted
Future-state design: intake | M3: Design | 2026-08-21 | Signed off by intake supervisor and ops director | In Progress
Future-state design: picking | M3: Design | 2026-08-25 | Signed off by DC managers at both sites | In Progress
Future-state design: shipping | M3: Design | 2026-08-28 | Signed off by shipping leads | In Progress
WMS configuration recommendations | M3: Design | 2026-09-01 | Each change tested in sandbox with before/after metrics | In Progress
Benefits model | M4: Roadmap | 2026-09-04 | Finance controller validates savings assumptions | In Progress
Costed improvement roadmap | M4: Roadmap | 2026-09-08 | Every initiative has owner, cost, and payback period | In Progress
Executive readout | M4: Roadmap | 2026-09-11 | Delivered to steering committee; questions answered in session | In Progress
Engagement closeout memo | M4: Roadmap | 2026-09-15 | Open items, handoffs, and follow-on options documented | In Progress
Acceptance progress |  |  | 2 of 12 deliverables accepted