## Full Stakeholder Register
Stakeholder | Title | Organization | Category | Influence | Engagement | Notes
Helen Cho | Chief Operating Officer | Alderwood Health | Sponsor | High | Champion | Owns the business case; monthly 1:1
Bruno Keller | Chief Information Officer | Alderwood Health | Executive | High | Supportive | Signs off architecture and security
Diane Foster | VP Patient Experience | Alderwood Health | Executive | High | Champion | Voice of the patient councils
Samir Qureshi | Program Manager | Alderwood Health | Team | Medium | Champion | Day-to-day delivery lead
Lotte Brandt | Clinic Operations Director | Alderwood Health | Executive | Medium | Neutral | Worried about front-desk workload during rollout
Ewan Macrae | Compliance Officer | Alderwood Health | Regulator | High | Neutral | HIPAA review gates each release
Pria Nathan | Nursing Informatics Lead | Alderwood Health | Team | Medium | Supportive | Runs clinical workflow validation
Carla Jimenez | Implementation Director | Meditech Partners | Vendor | Medium | Supportive | Contract renewal in November
Stefan Wolf | Integration Architect | Meditech Partners | Vendor | Low | Supportive | HL7 interface owner
Joy Adeyemi | Patient Advisory Council Chair | Alderwood Health | End User | Low | Champion | Recruits pilot patients
Marta Silva | Front Desk Supervisor, Eastside | Alderwood Health | End User | Low | Resistant | Burned by the last portal rollout; needs early wins
Gene Park | Finance Controller | Alderwood Health | Executive | Medium | Neutral | Tracks benefits realization
Ruth Ellison | Privacy Counsel | Alderwood Health | Regulator | Medium | Neutral | Reviews consent language
Andre Boucher | Service Desk Manager | Alderwood Health | Team | Low | Supportive | Owns tier-1 support scripts