## Power _ Interest Classification
Stakeholder | Power (1-5) | Interest (1-5) | Quadrant | Engagement Strategy
Helen Cho | 5 | 5 | Manage Closely | Weekly delivery note plus monthly steering chair
Bruno Keller | 5 | 3 | Manage Closely | Architecture checkpoints; escalation path for risks
Diane Foster | 4 | 5 | Manage Closely | Co-present patient-facing decisions with her team
Samir Qureshi | 3 | 5 | Manage Closely | Daily standup owner; no extra comms needed
Lotte Brandt | 4 | 2 | Keep Satisfied | Quarterly ops impact review; keep changes predictable
Ewan Macrae | 4 | 3 | Manage Closely | Compliance review booked per release train
Pria Nathan | 2 | 5 | Keep Informed | Working-group member; involve in every pilot
Carla Jimenez | 3 | 4 | Manage Closely | Monthly vendor governance call
Stefan Wolf | 2 | 4 | Keep Informed | Technical working group; interface change notices
Joy Adeyemi | 1 | 5 | Keep Informed | Pilot updates and recognition; she amplifies wins
Marta Silva | 2 | 2 | Monitor | Site visit before each rollout wave
Gene Park | 3 | 2 | Keep Satisfied | Benefits dashboard shared monthly