## Stakeholder Communications Plan
Stakeholder | Group | Channel | Frequency | Owner | Purpose | Next Touchpoint
Helen Cho | Executive sponsors | Steering meeting | Monthly | Samir Qureshi | Decisions, budget, top risks | 2026-07-28
Bruno Keller | Executive sponsors | 1:1 | Biweekly | Samir Qureshi | Architecture and security checkpoints | 2026-07-16
Diane Foster | Executive sponsors | Steering meeting | Monthly | Samir Qureshi | Patient experience metrics | 2026-07-28
Lotte Brandt | Clinic operations | 1:1 | Monthly | Samir Qureshi | Rollout impact on front-desk workload | 2026-07-21
Ewan Macrae | Compliance | Email update | At milestones | Samir Qureshi | Release compliance sign-off | 2026-08-03
Pria Nathan | Clinical working group | Steering meeting | Weekly | Pria Nathan | Workflow validation and pilot feedback | 2026-07-14
Carla Jimenez | Vendor governance | Steering meeting | Monthly | Samir Qureshi | Contract milestones, escalations | 2026-07-30
Stefan Wolf | Vendor technical | Email update | Biweekly | Pria Nathan | Interface changes and cutover windows | 2026-07-17
Joy Adeyemi | Patient advisory council | Town hall | Monthly | Diane Foster | Pilot recruitment and feedback loop | 2026-08-05
Marta Silva | Site staff | Town hall | At milestones | Lotte Brandt | Wave-by-wave rollout briefing | 2026-08-10
Gene Park | Finance | Dashboard | Monthly | Samir Qureshi | Benefits realization tracking | 2026-07-31
Andre Boucher | Support | Email update | Weekly | Pria Nathan | Known issues and support scripts | 2026-07-13